## Project Plan
| Project Start Date | 2024-01-29 | [5 empty] | 2024-01-29 | [6 empty] | 2024-02-05 | [6 empty] | 2024-02-12 | [6 empty] | 2024-02-19 | [6 empty] | 2024-02-26 | [6 empty] | 2024-03-04 | [6 empty] | 2024-03-11 | [6 empty] | 2024-03-18 | [6 empty] | 2024-03-25 | [6 empty] | 2024-04-01
| Project Name | Real time data warehousing with Airflow (F1 Data) |  |  |  | Week Starting | time axis 2024-01-29 to 2024-04-07
# | Activity | Owner | Start | End | Days | Status | % Completion | time axis 2024-01-29 to 2024-04-07
1 | project kick-off | hamsa | 2024-01-29 | 2024-01-29 | 1 | Complete | 100%
2 | requirements | hamsa | 2024-01-29 | 2024-02-02 | 5 | Complete | 100%
3 | design | hamsa | 2024-02-01 | 2024-02-07 | 5 | Complete | 100%
4 | build | hamsa | 2024-02-08 | 2024-03-17 | 30 | Complete | 100%
5 | unit testing | hamsa | 2024-02-12 | 2024-03-20 | 28 | Complete | 100%
6 | documentation | hamsa | 2024-03-20 | 2024-04-05 | 13 | Complete | 100%
7 | integration | hamsa | 2024-03-11 | 2024-03-27 | 13 | Complete | 100%
8 | final demo | hamsa | 2024-04-03 | 2024-04-03 | 1 | Complete | 100%
Status
Not Started
InProgress
Blocked
Complete

## 26-Jan
| MSc Project Discussion | 3:30-4PM
Minutes of meeting:
1 | Group discussion for all students whose projects are supervised by Professor Andrew Cobley
2 | I was advised by Professor to go through FastF1 library before the next meet on 29-Jan.
3 | To prepare a Gantt chart for project management

## 29-Jan
| MSc Project Discussion | 1-1:30PM
Minutes of meeting:
1 | Requirements discussion with Professor
2 | Review of Gantt chart by Professor. Professor Inputs: Timelines are not confirmed, however spanning it till the end of March seems quite right at this point.
3 | Professor has advised to prepare sun models with measures and dimensions to kick off the implementation

## 5-Feb
| MSc Project Discussion | 2:30-3PM
Minutes of meeting:
1 | I have worked on preparing a initial sun model, however the measures and dimensions aren't very clear at this point.
2 | Initial sun model is presented to the professor.
3 | Professor has advised to consider one model and start the system design and implementation

## 12-Feb
| MSc Project Discussion | 2:30-3PM
Minutes of meeting:
1 | I have a better understanding of the data model as the data necessary for the project is clearer now.
2 | I have updated the sun model with improved representation and reduced the complexity. Professor has approved this.
3 | I have also designed initial architecture where I have decided to implement the whole project in AWS and use the AWS services as required. I have discussed the same with professor and he has approved the implementation
4 | I have also checked with Professor for the AWS credits, he has confirmed he can check about the adding some credits if necessary.

## 19-Feb
| MSc Project Discussion | 2-2:30PM
Minutes of meeting:
1 | Started implementation inline with the approved design.
2 | I have adopted terraform to provision resources in the cloud
3 | I have discussed the problem with Professor reagrding the necessary permissions in AWS IAM to use the MWAA. However, he has confirmed that this is not a possibility and I may have to work with 3rd party softwares to implement the porject.
4 | I have tried an alternate, where in I have tried installing apache airflow as a docker container in a AWS EC2 instance. This is working alright. I have discussed the same with professor and he has approved that I can continue with this approach.
5 | The updated system design is approved by the professor and implementation of DAGs to establish a ETL pipeline is to be implemented

## 4-Mar
| MSc Project Discussion | 2-2:30PM
Minutes of meeting:
1 | Apache Airflow DAG to establish ETL workflow is complete and the event schedule and session details are queried successfully.
2 | The DAGs are to be updated to connect to the AWS Redshift and create tables and load the transformed data, thereby automating the ETL pipeline

## 18-Mar
| MSc Project Discussion | 2-2:30PM
Minutes of meeting:
1 | Apache Airflow DAG to establish ETL workflow is complete and the event schedule and session details are queried successfully.
2 | The DAGs are updated to connect to the AWS Redshift and create tables and load the transformed data
3 | Professorhas advised to complete the data analysis and start on the project report

## 27-Mar
| MSc Project Discussion | 2:30-3PM
Minutes of meeting:
1 | Data analysis and visualisations are complete. Discussed and presented this to Professor.
2 | Also discussed the issue where FastF1 API is unable to retrieve telemetry driver related information when batch query is run. This works for a particular race. To progress with the analysis and visualisation, I have triggered API query to Ergast via FastF1 library.
3 | Professor has advised to start on the report.

## 2-Apr
| MSc Project Discussion | 1:30-2PM
Minutes of meeting:
1 | Professor will check on poster availability and send a note
2 | Discussed on the sections of report I had queries, Professor has provided necessary clarification.
3 | Thanked professor for his guidance through out the project.